## Sheet1
Test ID | Requirement ID(s) | Test Procedure | Current Status | Last Time Tested | Build Version
1 | 1 | Integration / Security Test of the Account Creation Function | Passing | 2020-05-16 | Version 3.0.0 | Testing Statistics (as of 16MAY2020)
2 | 1.1 | Unit Test to ensure users provide a username | Passing | 2020-05-16 | Version 3.0.0 | Pass Rate | # Passing | #Not Passing | # Not Tested | Total Tests
3 | 1.1.1, 2.1 | Unit Test to ensure a username is not already taken | Not Tested |  |  | 46.08% | 47 | 0 | 55 | 102
4 | 1.2, 4.2 | Unit Test to ensure users provide an email | Passing | 2020-05-16 | Version 3.0.0
5 | 1.2.1, 4.2 | Unit Test to ensure the user's email is a valid email | Not Tested
6 | 1.2.2, 2.3.1.1, 4.2 | Unit Test to verify that the user's email is not already taken by another user | Not Tested
7 | 1.3, 1.3.1 | Unit Test to ensure the user supplies a password | Passing | 2020-05-16 | Version 3.0.0
8 | 1.3.2 | Usability Test of the ability to hide password entries | Passing | 2020-05-16 | Version 3.0.0
9 | 1.3.3, 4.3.3 | Inspection Unit Test to ensure passwords meet strength criteria | Not Tested
10 | 1.3.3.1, 4.3.3 | Unit Test to verify passwords are at least 15 characters in length | Not Tested
11 | 1.3.3.2, 4.3.3 | Unit Test to verify that passwords contain at least one upper case letter | Not Tested
12 | 1.3.3.3, 4.3.3 | Unit Test to verify that passwords contain at least one lower case letter | Not Tested
13 | 1.3.3.4, 4.3.3 | Unit Test to verify that passwords contain at least one number | Not Tested
14 | 1.3.3.5, 4.3.3 | Unit Test to verify that passwords contain at least one symbol | Not Tested
15 | 1.4, 4.1 | Unit Test of the ability to select trainer icon picture | Not Tested
16 | 2 | Integration / Security Test of the log-on function | Passing | 2020-05-16 | Version 3.0.0
17 | 2.2 | Unit Test to verify the given password is associated with an active acount | Passing | 2020-05-16 | Version 3.0.0
18 | 2.2.1 | Unit Test to verify that the given password matches the selected user profile's password on record | Passing | 2020-05-16 | Version 3.0.0
19 | 2.3, 4.3 | Integration Test of password change functionality | Passing | 2020-05-16 | Version 3.0.0
20 | 2.3.1 | Unit Test to verify users have entered an email before changing passwords | Not Tested
21 | 2.3.1.2 | Unit Test to verify a one-time link is generated to enable password reset | Not Tested
22 | 3 | System Test to verify the account summary page functions correctly | Passing | 2020-05-16 | Version 3.0.0
23 | 3.1 | Unit Test to verify the user's username, email, and trainer icon are displayed | Passing | 2020-05-16 | Version 3.0.0
24 | 3.2 | Integration testing to verify that the trainer's battle record is properly displayed | Not Tested
25 | 3.3 | Integration Test to verify that the user's saved Pokémon are displayed properly | Not Tested
26 | 3.4 | Integration Test to verify that the user's saved teams are displayed properly | Passing | 2020-05-16 | Version 3.0.0
27 | 4 | Integration Test to verify that user's are able to update all aspects of their account | Passing | 2020-05-16 | Version 3.0.0
28 | 4.3.1 | Unit Test to verify that users enter their current, correct password before changing to a new password | Passing | 2020-05-16 | Version 3.0.0
29 | 4.3.2 | Unit Test to ensure users are required to enter their new password twice before recording the new change (and that the two entries match each other) | Passing | 2020-05-16 | Version 3.0.0
30 | 5 | Usability Testing to ensure a consistent navigation and display experience throughout the application | Passing | 2020-05-16 | Version 3.0.0
31 | 5.1 | Usability Testing to ensure there is a navigation tree on all pages | Passing | 2020-05-16 | Version 3.0.0
32 | 5.2 | Usability Testing to ensure the navigation tree is in the same position on all pages | Passing | 2020-05-16 | Version 3.0.0
33 | 5.3 | Usability Testing to verify that the color scheme is the same on all pages | Passing | 2020-05-16 | Version 3.0.0
34 | 5.4 | Usability Testing to verify that the font style and size is consistent throughout the application | Passing | 2020-05-16 | Version 3.0.0
35 | 5.5 | Usability Testing to verify that the system uses the same art style for all Pokémon images | Not Tested
36 | 5.6 | Usability Testing to verify that all images in the same element are the same size/dimensions | Not Tested
37 | 6 | Integration / System Testing to verify that Pokémon and teams marked public are searchable to other users | Passing | 2020-05-16 | Version 3.0.0
38 | 6.1 | Unit Test to ensure there is an option to mark a team design as public | Passing | 2020-05-16 | Version 3.0.0
39 | 6.2 | Unit Test to ensure there is an option to mark a Pokémon design as public | Not Tested
40 | 7 | Integration Test of the Pokémon search funationality | Passing | 2020-05-16 | Version 3.0.0
41 | 7.1, 10.1 | Unit Test to verify that users can search by Pokémon name | Passing | 2020-05-16 | Version 3.0.0
42 | 7.2, 10.1 | Unit Test to verify that users can search by Pokémon number | Not Tested
43 | 7.3 | Unit Test to verify that users can search by Pokémon type(s) | Passing | 2020-05-16 | Version 3.0.0
44 | 7.4 | Unit Test to verify that users can search by Pokémon ability | Not Tested
45 | 7.5 | Unit Test to verify that users can search by Pokémon moves | Not Tested
46 | 7.6 | Unit Test to verify that users can search by Pokémon stat levels | Not Tested
47 | 7.7 | Unit Test to verify that users can search by Pokémon the username of the user who created a custom version of that specific Pokémon | Not Tested
48 | 8 | Integration Test of the Pokémon display funationality | Passing | 2020-05-16 | Version 3.0.0
49 | 8.1 | Unit Test to verify the system displays the Pokémon’s name | Passing | 2020-05-16 | Version 3.0.0
50 | 8.2 | Unit Test to verify the system displays the Pokémon’s number | Passing | 2020-05-16 | Version 3.0.0
51 | 8.3 | Unit Test to verify the system displays the Pokémon’s type(s) | Passing | 2020-05-16 | Version 3.0.0
52 | 8.4 | Unit Test to verify the system displays the Pokémon’s ability(ies) | Not Tested
53 | 8.5 | Unit Test to verify the system displays the Pokémon’s available moves | Not Tested
54 | 8.6 | Unit Test to verify the system displays the Pokémon’s base stat levels for all stat categories | Passing | 2020-05-16 | Version 3.0.0
55 | 8.7 | Unit Test to verify the system displays the Pokémon’s Pokédex entry | Not Tested
56 | 9 | Integration Test of the Pokémon customization feature | Not Tested
57 | 9.1 | Integration Test to ensure the system allows users to change a Pokémon's ability | Not Tested
58 | 9.1.1 | Unit Test to verify that users may only select abilities that the Pokémon is allowed to have | Not Tested
59 | 9.2 | Integration Test of the type-change functionality | Not Tested
60 | 9.2.1 | Unit Test to verify that the Pokémon actually has different forms with different types | Not Tested
61 | 9.2.1.1 | Unit Test to verify users can select which form of a Pokémon they want to select | Not Tested
62 | 9.3 | Integration Test to ensure users can assign four unique moves to the Pokémon | Not Tested
63 | 9.3.1 | Unit Test to restrict the moves available for selection to those moves that the Pokémon can actually learn | Not Tested
64 | 9.4 | Unit Test to verify that users are able to assign an item to a Pokémon to hold | Not Tested
65 | 9.4.1 | Unit Test that verifies the Pokémon can only hold one item at a time | Not Tested
66 | 9.5 | Integration Test to verify the nature change functionality works properly | Not Tested
67 | 9.6 | Integration Test to verify that users can adjust the effort values of a Pokémon | Not Tested
68 | 9.7 | Integration Test to verify that users can adjust the individual values of a Pokémon | Not Tested
69 | 9.8 | Unit Test of the save function | Not Tested
70 | 9.8.1 | Unit Test to ensure the system generates a unique ID number for every customized Pokémon | Not Tested
71 | 9.8.2 | Unit Test to ensure the system provides users the option to assign the customized Pokémon a nickname | Not Tested
72 | 10 | Integration Test of the team creation functionality | Passing | 2020-05-16 | Version 3.0.0
73 | 10.2 | Unit Test to verify that users can search for a Pokémon from their list of saved custom Pokémon | Not Tested
74 | 10.3 | Unit Test to verify that the system generates a unique ID number for each saved team | Passing | 2020-05-16 | Version 3.0.0
75 | 10.4 | Unit Test to verify that the system provides users the option to assign the team a nickname | Passing | 2020-05-16 | Version 3.0.0
76 | 10.5 | Integration Test to verify that the team is a valid team | Passing | 2020-05-16 | Version 3.0.0
77 | 10.5.1 | Unit Test to verify that only one version of each Pokémon is present on the team | Passing | 2020-05-16 | Version 3.0.0
78 | 10.5.2 | Unit Test to verify that only one copy of each item is present on the team | Not Tested
79 | 11 | Integration Test to verify the user is able to search for and find a team that was marked as public | Passing | 2020-05-16 | Version 3.0.0
80 | 11.1 | Unit Test to verify users can search for teams by the unique team ID | Not Tested
81 | 11.2 | Unit Test to verify users can search for teams by the team name | Not Tested
82 | 11.3 | Unit Test to verify users can search for teams by the creator's username | Not Tested
83 | 11.4 | Unit Test to verify users can search for teams by the Pokémon on the team | Not Tested
84 | 12 | System Test to verify that the application provides correct analysis of the strengths/weaknesses of a 6-Pokémon team | Passing | 2020-05-16 | Version 3.0.0
85 | 12.1, 13.2.1, 14.2, 15.2 | Integration Test to verify the net weaknesses/strengths/resistances match the predictive analysis | Passing | 2020-05-16 | Version 3.0.0
86 | 12.1.1, 13.2.1, 14.2, 15.2 | Unit Test to verify that the application has counted the number of type-advantages that the team has | Passing | 2020-05-16 | Version 3.0.0
87 | 12.1.2, 13.2.1, 14.2, 15.2 | Unit Test to verify that the application has counted the number of type-weaknesses that the team has | Passing | 2020-05-16 | Version 3.0.0
88 | 12.1.3, 13.2.1, 14.2, 15.2 | Unit Test to verify that the application has counted the number of type-resistances that the team has | Passing | 2020-05-16 | Version 3.0.0
89 | 12.1.4, 13.2.1, 14.2, 15.2 | Unit Test to verify that the application has properly calculated the net total strengths/weaknesses/resistances | Passing | 2020-05-16 | Version 3.0.0
90 | 12.2, 13.2.1, 14.2, 15.2 | Integration Test to verify that the application correctly calculates the average base total of the team | Passing | 2020-05-16 | Version 3.0.0
91 | 12.2.1, 13.2.1, 14.2, 15.2 | Unit Test to ensure all 6 Pokémon's base stat total is included in the team average calculation | Passing | 2020-05-16 | Version 3.0.0
92 | 13 | System Test to verify that the application correctly generates all possible team combinations and analyzes them properly | Passing | 2020-05-16 | Version 3.0.0
93 | 13.1, 14.1, 15.1 | Unit Test to verify that the user has entered a full 6-Pokémon team for analysis | Passing | 2020-05-16 | Version 3.0.0
94 | 13.2, 15.3, 15.4 | Unit Test to verify that all 15 possible combinations have been generated | Passing | 2020-05-16 | Version 3.0.0
95 | 14 | System Test to verify that the application correctly generates an appropriate 6-Pokémon, given an opponent's 6-Pokémon team | Not Tested
96 | 14.3 | Integration Test to verify the application generates an appropriate 6-Pokémon that compliments the strengths/weaknesses of the opponent's team | Not Tested
97 | 15 | System Test to verify that the application generates an appropriate 4-Pokémon team to counter an opponent's predicted team | Not Tested
98 | 16 | Integration Test to verify the application provides a diaply to track information during a match | Not Tested
99 | 16.1 | Unit Test to verify each battle in the match has its own display section | Not Tested
100 | 16.2 | Unit Test to ensure the player's and opponent's 6-Pokémon teams are displayed separately from the 4-Pokémon teams brought for each battle in the match | Not Tested
101 | 16.3 | Unit Test to verify there is an interface that enables the user to enter which Pokémon the opponent brought to the battle | Not Tested
102 | 16.3.1 | Unit Test to verify that the application allows users to enter the revealed moves, items, and abilities of each Pokémon brought to each battle | Not Tested